## Project Gantt Chart
Project gantt chart
Task ID | Task Name | Planned Duration (days) | Assigned group member(s)
T1 | Complete task delivery form | 14 | Connor Hill
T2 | Complete Gantt Chart | 14 | Connor Hill
T3 | Complete use-case diagram | 14 | Whole group
T4 | Set-up and connect database | 14 | William Blackie, Jake Chapman
T5 | Develop login function | 14 | Connor Hill, Jonas Arud
T6 | Test login function | 14 | Tom Vanlaer-McCanna
T7 | Weekly sprint review | 14 | Whole group
T8 | Produce sprint presentation | 14 | Whole group
T9 | Complete task delivery form 2 | 1 | Whole group
T10 | Update Gantt Chart 2 | 2 | Whole group
T11 | Graphical implementation of customer access | 14 | Connor Hill, Tom Vanlaer-McCanna
T12 | Graphical implementation of head office access | 14 | William Blackie, Jake Chapman
T13 | Graphical implementation of driver access | 14 | Jonas Arud
T14 | Weekly sprint review | 7 | Whole group
T15 | Commit review | 14 | Whole group
T16 | Handle session timeout | 7 | William Blackie
T17 | Finalise user interface/house style | 7 | Connor Hill
T18 | Design and add logo | 1 | Tom Vanlaer-McCanna
T19 | Complete task delivery form 3 | 1 | Whole group
T20 | Update Gantt Chart 3 | 1 | Whole group
T21 | implement google maps api | 7 | Connor Hill and Tom Vanlaer-McCanna
T22 | Implement customer confirmation | 7 | Connor Hill and Tom Vanlaer-McCanna
T23 | Implement driver history | 7 | William Blackie
T24 | Implement job completion | 7 | Connor Hill and William Blackie
T25 | Implement driver editing | 7 | William Blackie
T26 | Complete webservice Testing | 7 | Whole group
T27 | Update SQL | 7 | Whole group
T28 | Implement customer editing | 7 | William Blackie
T29 | Fix driver registarion | 7 | Jonas Arud
T30 | Implement customers served per day | 7 | Tom Vanlaer-McCanna
T31 | Implement daily turnover | 7 | Jonas Arud
T32 | Assign jobs to driver | 7 | Tom Vanlaer-McCanna
T33 | Complete testing | 2 | Whole group
T34 | Project sign-off | 1 | Whole group
Colour | Type
Actual
Planned
Task | Planned Start | Planned Duration (days) | Actual Start | Actual Duration (days) | Percent Complete | time axis 2018-10-29 to 2018-12-10
T1 | 2018-10-29 | 14 | 2018-10-29 | 1 | 100%
T2 | 2018-10-29 | 14 | 2018-10-29 | 1 | 100%
T3 | 2018-10-29 | 14 | 2018-10-29 | 1 | 100%
T4 | 2018-10-29 | 14 | 2018-10-29 | 7 | 100%
T5 | 2018-10-29 | 14 | 2018-10-29 | 11 | 100%
T6 | 2018-10-29 | 14 | 2018-10-29 | 13 | 100%
T7 | 2018-11-04 | 7 | 2018-11-04 | 1 | 100%
T8 | 2018-11-04 | 7 | 2018-11-04 | 7 | 100%
T9 | 2018-11-25 | 1 | 2018-11-25 | 1 | 100%
T10 | 2018-11-12 | 2 | 2018-11-24 | 14 | 75%
T11 | 2018-11-12 | 14 | 2018-11-12 | 12 | 100%
T12 | 2018-11-12 | 14 | 2018-11-12 | 5 | 100%
T13 | 2018-11-12 | 14 | 2018-11-12 | 12 | 100%
T14 | 2018-11-19 | 7 | 2018-11-19 | 1 | 100%
T15 | 2018-11-19 | 14 | 2018-11-19 | 1 | 100%
T16 | 2018-11-12 | 7 | 2018-11-12 | 1 | 100%
T17 | 2018-11-12 | 7 | 2018-11-12 | 2 | 100%
T18 | 2018-11-19 | 7 | 2018-11-19 | 1 | 100%
T19 | 2018-11-26 | 1 | 2018-11-26 | 1 | 100%
T20 | 2018-11-26 | 1 | 2018-11-26 | 1 | 100%
T21 | 2018-11-26 | 10 | 2018-11-26 | 7 | 100%
T22 | 2018-11-26 | 10 | 2018-11-26 | 7 | 100%
T23 | 2018-11-26 | 5 | 2018-11-26 | 5 | 100%
T24 | 2018-11-26 | 5 | 2018-11-26 | 5 | 100%
T25 | 2018-11-26 | 7 | 2018-11-26 | 6 | 100%
T26 | 2018-11-26 | 10 | 2018-11-26 | 9 | 100%
T27 | 2018-11-26 | 3 | 2018-11-26 | 2 | 100%
T28 | 2018-11-26 | 5 | 2018-11-26 | 6 | 100%
T29 | 2018-11-26 | 1 | 2018-11-26 | 2 | 100%
T30 | 2018-11-26 | 3 | 2018-11-26 | 7 | 100%
T31 | 2018-11-26 | 2 | 2018-11-26 | 1 | 100%
T32 | 2018-11-26 | 2 | 2018-11-26 | 3 | 100%
T33 | 2018-12-29 | 7 | 2018-12-29 | 7 | 100%
T34 | 2018-12-05 | 1 | 2018-12-05 | 1 | 100%

## Sheet1
Task ID | Task Name | Planned Duration (Periods) | Assigned group member(s) | Task ID | Task Name | Planned Duration (Periods) | Assigned group member(s) | Task ID | Task Name | Planned Duration (Periods) | Assigned group member(s)
T1 | Complete task delivery form | 2 | Connor Hill | T1 | Complete task delivery form | 2 | Connor Hill | T1 | Complete task delivery form | 2 | Connor Hill
T2 | Complete Gantt Chart | 2 | Connor Hill | T2 | Complete Gantt Chart | 2 | Connor Hill | T2 | Complete Gantt Chart | 2 | Connor Hill
T3 | Complete use-case diagram | 2 | Whole group | T3 | Complete use-case diagram | 2 | Whole group | T3 | Complete use-case diagram | 2 | Whole group
T4 | Set-up and connect database | 2 | William Blackie, Jake Chapman | T4 | Set-up and connect database | 2 | William Blackie, Jake Chapman | T4 | Set-up and connect database | 2 | William Blackie, Jake Chapman
T5 | Develop login function | 2 | Connor Hill, Jonas Arud | T5 | Develop login function | 2 | Connor Hill, Jonas Arud | T5 | Develop login function | 2 | Connor Hill, Jonas Arud
T6 | Test login function | 2 | Tom Vanlaer-McCanna | T6 | Test login function | 2 | Tom Vanlaer-McCanna | T6 | Test login function | 2 | Tom Vanlaer-McCanna
T7 | Weekly sprint review | 2 | Whole group | T7 | Weekly sprint review | 2 | Whole group | T7 | Weekly sprint review | 2 | Whole group
T8 | Produce sprint presentation | 1 | Whole group | T8 | Produce sprint presentation | 1 | Whole group | T8 | Produce sprint presentation | 1 | Whole group